## Risk Register
TLP:RED — NAMED RECIPIENTS ONLY — Do not distribute outside the named project group
defecia.dk — Risk Analysis Register
Organisation: | defecia.dk |  |  |  | Revision: | X.X
Date: | [DATE] |  |  |  | Owner: | [Name / Department]
Risk Factor | Likelihood (1–5) | Consequence (1–5) | Risk Score S × K | Priority | Mitigating Actions | Likelihood After Mitigation | Consequence After Mitigation | Residual Risk Score | Status
| 1=Rare 5=Almost certain | 1=Negligible 5=Catastrophic | Formula: B×C | Auto from score |  | 1=Rare 5=Almost certain | 1=Negligible 5=Catastrophic | Formula: G×H | Open / In Progress / Closed
Cloud service login attack | 5 | 5 | 25 | CRITICAL | Implement MFA for all accounts. Enforce strong password policy. Monitor failed logins. | 1 | 5 | 5 | In Progress
Ransomware via phishing email | 4 | 5 | 20 | CRITICAL | Email filtering + sandboxing. Endpoint protection (EDR). Regular offline backups. User awareness training. | 2 | 4 | 8 | In Progress
Unauthorised data access by insider | 3 | 4 | 12 | HIGH | Role-based access control (RBAC). Privileged access management (PAM). User activity logging. | 2 | 3 | 6 | Open
Unpatched vulnerability exploited | 4 | 4 | 16 | HIGH | Monthly patch management cycle. Vulnerability scanning. Critical CVEs patched within 48h. | 1 | 4 | 4 | In Progress
Third-party supplier breach | 3 | 4 | 12 | HIGH | Vendor security questionnaire. Contractual security requirements. Regular review. | 2 | 3 | 6 | Open
DDoS attack on web services | 3 | 3 | 9 | MEDIUM | CDN with DDoS protection. Rate limiting. Incident response plan. | 1 | 3 | 3 | Closed
Lost or stolen laptop | 3 | 2 | 6 | MEDIUM | Full-disk encryption (BitLocker/FileVault). MDM remote wipe. Screen lock policy. | 1 | 2 | 2 | Closed
Accidental data deletion | 2 | 3 | 6 | MEDIUM | Automated daily backups. Versioning enabled. Restore testing quarterly. | 1 | 2 | 2 | Open
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
|  |  | 0 |  |  |  |  | 0
RISK SCORE LEGEND (Likelihood × Consequence)
CRITICAL | Score 20–25 | Immediate action required. Escalate to C-level.
HIGH | Score 12–19 | Action required within 1 week. Assign owner.
MEDIUM | Score 6–11 | Action required within 1 month. Document progress.
LOW | Score 1–5 | Monitor. Review annually or when context changes.
SCORING GUIDE
Likelihood Scale |  |  |  |  | Consequence Scale
1 | Rare |  | May occur only in exceptional circumstances (< once in 10 years) |  | 1 | Negligible |  | Minimal impact. No disruption to operations. No data loss.
2 | Unlikely |  | Could occur at some time (once in 3–10 years) |  | 2 | Minor |  | Small impact. Short disruption. Contained data issue.
3 | Possible |  | Might occur at some time (once in 1–3 years) |  | 3 | Moderate |  | Significant impact. Noticeable disruption or data breach.
4 | Likely |  | Will probably occur in most circumstances (once per year or more) |  | 4 | Major |  | Serious impact. Extended outage. Significant data or financial loss.
5 | Almost Certain |  | Expected to occur in most circumstances (multiple times per year) |  | 5 | Catastrophic |  | Existential impact. Critical systems down. Major breach or regulatory action.
Educational purpose by Lars Blomgaard — CC BY 4.0 — xleb@defecia.dk

## Risk Heatmap
TLP:RED — NAMED RECIPIENTS ONLY
defecia.dk — 5×5 Risk Heatmap
The heatmap shows all possible combinations of Likelihood (rows) × Consequence (columns). Each cell shows the Risk Score (Likelihood × Consequence). Colour coding matches the Risk Register.
Likelihood ↓ / Consequence → | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic | Risk Treatment Strategies
5 Almost Certain | 5 | 10 | 15 | 20 | 25 | AVOID | Eliminate the activity or condition that creates the risk.
4 Likely | 4 | 8 | 12 | 16 | 20 | REDUCE | Implement controls to lower likelihood or consequence.
3 Possible | 3 | 6 | 9 | 12 | 15 | TRANSFER | Share or transfer the risk (insurance, contract, outsource).
2 Unlikely | 2 | 4 | 6 | 8 | 10 | ACCEPT | Acknowledge the risk and document acceptance with owner sign-off.
1 Rare | 1 | 2 | 3 | 4 | 5
Note for larger organisations: This simplified 5×5 matrix is based on ISO 31000 and ISO 27005 principles. NIS2 Article 21 requires systematic risk management for essential and important entities. Larger organisations typically add: Risk Owner, Risk Appetite threshold, Treatment deadline, and Evidence of control effectiveness.
LEGEND
CRITICAL | Score 20–25
HIGH | Score 12–19
MEDIUM | Score 6–11
LOW | Score 1–5
Educational purpose by Lars Blomgaard — CC BY 4.0 — xleb@defecia.dk